## Sheet1
Item/function	Potential Failure Mode	Potential Cause	Potential Effect(s) of Failure	Current Design Controls	Further Action
prop	smashed	wind, waves, rocks	loss of control/DNF	impact resistant material, glass reenforced
Battery	depleted	too small	loss of control/DNF/no dive	Use proper battery	DOE on battery life
ignitor	no ignition	wind interferes with ignition	Lost Points	wind guard
		ignitor fails		Using commercial solid wire tungstin element
		battery depleted		Using pwc control
		does not ignite		Using butane with low autoignion point
jaw	does not open	battery depleted	Lost Points

Drive unit	does not turn	battery depleted	loss of control/DNF/no dive
	Clutch slippage	wrong setting	poor speed/no dive	will test and lock
	Lose comm when dive	weak signal	resurfacing/lost points	Using 27 MHz control
	O ring pops out of groove	Too flexible	leak/motordamage